## WIN Support Dates
WIN Learning Training and Support: SY2014-15
Middle and High Schools
|  | Updated 5/19/15 | [7 empty] | Optional
Coop | District | School | Preliminary Implementation Communication | Implementation Planning Meeting | Technology Readiness Assessment | Onsite Support Visit 1 | Virtual Support 1 | Onsite Support Visit 2 | Virtual Support 2 | Onsite Support Visit 3 | Onsite Support Visit 4
GRREC | Adair County | Adair County High School | 2014-09-30 | 2014-10-21 | 2014-10-21 | 2014-10-21 | 10/30, 11/17, 11/20, 12/10, 12/17, 12/30, 1/16 | 2015-03-25 |  | 2015-05-12
GRREC | Adair County | Adair County Elementary School | 2014-09-30 |  | 2014-10-21
GRREC | Adair County | Adair County Middle School | 2014-09-30 | 2014-11-21 | 2014-10-21 | 2014-10-21 |  | 2015-12-12
GRREC | Campbellsville | Campbellsville High School | 2014-09-05 | 2014-09-11 | 2014-11-06 | 2014-11-07 | 1/12, 1/13, 1/14 | 2015-01-09 | 2/5, 2/26 | 2015-04-13
GRREC | Campbellsville | Campbellsville Middle School | 2014-09-05 | 2014-09-11 | 2014-11-06 | 2014-11-07 | 2015-01-09 | 2015-01-09 | 2015-02-26
OVEC | Carroll County | Carroll County Middle School | 2014-08-22 | 2014-08-26 | 2014-10-18 | 2015-05-05 | 2015-08-27
OVEC | Carroll County | Carroll County High School | 2014-08-22 | 2014-08-26 | 2014-10-18 | 2014-11-20 | 9/16, 9/26, 11/20 | 2015-01-14 |  | 2015-05-05
GRREC | Caverna Ind. | Caverna High School | 2014-09-05 | 2014-09-09 | 2014-10-20 | 2014-10-31 |  | 2015-03-17
GRREC | Caverna Ind. | Caverna Middle School | 2014-09-05 | 2014-09-09 | 2014-10-20
GRREC | Cloverport Ind. | Frederick Fraize High School | 2014-10-01 | 2014-11-18 | 2014-11-13 | 2015-04-21 | 2015-12-14
GRREC | Cloverport Ind. | Frederick Fraize Middle School | 2014-10-01 | 2014-11-18 | 2014-11-13 | 2015-04-21 | 2015-12-14
GRREC | Daviess County | Apollo High School | 2014-10-01 | 2015-12-16 | 2014-10-02 | 2015-01-22 | 2015-01-21 | 2015-05-11 | 2/9, 2/11, 2/13, 2/23
GRREC | Daviess County | Daviess County High School | 2014-10-01 | 2014-12-16 | 2014-10-02 | 2015-01-22 | 12/18, 12/30 | 2015-05-11
GRREC | Daviess County | College View Middle School | 2014-10-01 | 2014-12-16 | 2014-10-02
GRREC | Daviess County | Daviess County Middle School | 2014-10-01 | 2014-12-16 | 2014-10-02 | 2015-01-22
GRREC | Daviess County | F T Burns Middle School | 2014-10-01 | 2014-12-16 | 2014-10-02
GRREC | Green County | Green County High School | 2014-08-28 | 2014-10-01 | 2014-10-01 | 2014-10-24 | 2015-01-13 | 2015-02-11 | 2015-02-05 | 2015-04-28
GRREC | Green County | Green County Middle School | 2014-09-09 | 2014-10-01 | 2014-10-01 | 2014-10-24
GRREC | Hart County | Hart County High School | 2014-09-10 | 2014-09-18 | 2014-10-29 | 2015-03-12 | 10/2, 10/31, 11/10, 1/14
GRREC | Hart County | Bonnieville Elementary School | 2014-09-10 | 2014-09-18 | 2014-10-29
GRREC | Hart County | Cub Run Elementary School | 2014-09-10 | 2014-09-18 | 2014-10-29
GRREC | Hart County | Legrande Elementary School | 2014-09-10 | 2014-09-18 | 2014-10-29
GRREC | Hart County | Memorial Elementary School | 2014-09-10 | 2014-09-18 | 2014-10-29
GRREC | Hart County | Munfordville Elementary School | 2014-09-10 | 2014-09-18 | 2014-10-29 |  | 2015-01-15
OVEC | Henry County | Henry County Middle School | 2014-08-22 | 2014-08-27 | 2014-12-04 | 2015-01-20
OVEC | Henry County | New Castle Elementary School | 2014-08-22 |  | 2014-12-04
OVEC | Henry County | Henry County High School | 2014-08-22 | 2014-08-27 | 2014-12-04 | 2015-01-15 | 2015-12-03 | 2015-06-03 | 2015-03-02
GRREC | Logan County | Logan County High School | 2014-10-01 | 2014-11-21 | 2015-01-27 | 2015-01-27 | 2015-01-28 | 2015-02-10 | 2015-04-20 | 2015-04-27
GRREC | Logan County | Adairville Elementary School | 2014-10-01: 2014-10-01; 2014-11-21: 2014-11-21; 2015-01-27: 2015-01-27
GRREC | Logan County | Auburn Elementary School | 2014-10-01 | 2014-12-18 | 2015-01-27 | 2015-01-16 |  | 2015-02-10 |  | 2015-03-03 | 2015-05-20
GRREC | Logan County | Chandlers Elementary School | 2014-10-01: 2014-10-01; 2014-11-21: 2014-11-21; 2015-01-27: 2015-01-27
GRREC | Logan County | Lewisburg Elementary School | 2014-10-01: 2014-10-01; 2014-11-21: 2014-11-21; 2015-01-27: 2015-01-27
GRREC | Logan County | Olmstead Elementary School | 2014-10-01: 2014-10-01; 2014-11-21: 2014-11-21; 2015-01-27: 2015-01-27
GRREC | Metcalfe County | Metcalfe County High School | 2014-09-29 | 2014-10-29 | 2014-10-24 | 2014-10-29 | 2015-12-15 | 2015-04-14 | 2015-02-19
GRREC | Metcalfe County | Metcalfe County Middle School | 2014-08-13 | 2014-10-29 | 2014-10-24 | 2014-10-29 |  | 2015-03-26
GRREC | Monroe County | Monroe County High School | 2014-09-29 | 2014-11-05 | 2014-10-29 | 2014-11-05 | 11/16, 11/19, 11/26, 12/3 | 2015-03-16
GRREC | Monroe County | Monroe County Middle School | 2014-09-29 | 2014-11-19 | 2014-10-29 | 2015-03-16 |  |  | 2015-02-03
OVEC | Owen County | Maurice Bowling Middle School | 2014-08-25 | 2014-09-24 | 2014-11-13 | 2014-10-13 |  | 2015-05-04
OVEC | Owen County | Owen County High School | 2014-08-25 | 2014-09-24 | 2014-11-13 | 2014-10-13 | 2015-10-17 | 2015-12-18 | 3/3, 3/9, 3/12 | 2015-05-04
GRREC | Owensboro Ind. | Owensboro High School | 2014-10-01 | 2014-12-16 | 2014-10-21 | 2015-03-23 | 9/25, 10/1 |  | 2015-03-09
GRREC | Owensboro Ind. | Owensboro Middle School North | 2014-10-01: 2014-10-01; 2014-11-21: 2014-12-16; 2015-01-27: 2014-10-21; 2015-01-27: 2015-01-22
GRREC | Owensboro Ind. | Owensboro Middle School South | 2014-10-01: 2014-10-01; 2014-11-21: 2014-12-16; 2015-01-27: 2014-10-21; 2015-01-27: 2015-01-22
GRREC | Russell County | Russell County High School | 2014-08-27 | 2014-09-05 | 2014-10-30 | 2014-10-28 | 9/8, 11/25 | 2015-01-21 |  | 2015-03-17
GRREC | Russell County | Jamestown Elementary School | 2014-10-01: 2014-08-27; 2014-11-21: 2014-09-05; 2015-01-27: 2014-10-30
GRREC | Russell County | Russell County Middle School | 2014-08-27 | 2014-09-05 | 2014-10-30 | 2014-10-28 | 9/29, 10/1 | 2015-01-21 | 2015-02-06 | 2015-03-17
GRREC | Russell County | Russell Springs Elementary School | 2014-10-01: 2014-08-27; 2014-11-21: 2014-09-05; 2015-01-27: 2014-10-30
GRREC | Russell County | Salem Elementary School (6) | 2014-10-01: 2014-08-27; 2014-11-21: 2014-09-05; 2015-01-27: 2014-10-30
OVEC | Shelby County | Shelby County East Middle School | 2014-10-01: 2014-08-14; 2014-11-21: 2014-08-18; 2015-01-27: TBD
OVEC | Shelby County | Shelby County West Middle School | 2014-10-01: 2014-08-14; 2014-11-21: 2014-08-18; 2015-01-27: TBD
OVEC | Shelby County | Martha Layne Collins High School | 2014-08-14 | 2014-08-18 | TBD | 2014-10-28 | 10/7, 10/9, 10/14 | 2015-02-12 | 2/3, 2/11 | 2015-03-10 | 2015-05-15
OVEC | Shelby County | Shelby County High School | 2014-08-14 | 2014-08-18 | TBD | 11/11, 1/15 | 10/3, 10/7, 11/11,11/19, 1/16 | 2015-02-24 | 3/4, 3/10, 3/24 | 2015-05-15
GRREC | Simpson County | Franklin-Simpson High School | 2014-10-01: 2014-08-25; 2014-11-21: 2014-08-26; 2015-01-27: TBD; 2015-01-27: 2015-11-18
GRREC | Simpson County | Franklin-Simpson Middle School | 2014-08-25 | 2014-08-26 | TBD |  | 2015-08-26 | N/A
OVEC | Spencer County | Spencer County Elementary School (K-5) | 2014-10-01: 2014-08-22; 2015-01-27: 2014-10-30
OVEC | Spencer County | Spencer County Middle School | 2014-08-22 | 2014-08-28 | 2014-10-30 | 2014-11-12 |  | 2015-02-23
OVEC | Spencer County | Spencer County High School | 2014-08-22 | 2014-08-28 | 2014-10-30 | 2014-11-12 |  | 2015-02-23 |  | 2015-05-08
GRREC | Taylor County | Taylor County High School | 2014-09-05 | 2014-09-11 | 2014-10-20 | 2014-10-22 | 10/20, 10/22, 10/27, 1/6, 1/21 | 2015-02-09 | 2/23, 3/2 | 2015-04-28
GRREC | Taylor County | Taylor County Middle School | 2014-09-05 | 2014-09-11 | 2014-10-20 | 2015-10-24 | 2015-10-22 | 2015-02-09
OVEC | Trimble County | Trimble County Middle School | 2014-08-22 | 2014-08-27 | 2014-10-24 | 2015-01-14 |  | 2015-02-03 | 2015-02-05 | 2015-04-21
OVEC | Trimble County | Trimble County High School | 2014-08-22 | 2014-08-27 | 2014-10-24 | 2015-01-14 | 9/15, 10/13 | 2015-04-21 | 2015-03-12
GRREC | Union County | Union County High School | 2014-08-19 | 2014-08-25 | 2014-10-10 | 2014-11-17 | 8/25, 1/12, 1/23, 1/26 | 2015-01-07 | 2/6, 4/13, 4/20 | 2015-03-24
GRREC | Union County | Union County Middle School | 2014-08-19 | 2014-08-25 | 2014-10-10 | 2014-11-17 | 11/19, 12/3, 1/26 | 1/9, 1/14 | 2/6, 2/9 | 2015-03-24
GRREC | West Point | West Point Middle School | 2014-09-29 | 2014-11-12 | 2014-11-05 | 2014-11-12 | 10/29, 11/23, 12/19, 1/8, 1/13 | 2015-03-12

## Progress and Final Reports
WIN Learning 2014-2015 Final Report
|  | As of 1/30/15 |  |  |  | As of 5/19/15
|  | Green | 24 (38%) |  |  | Green | 30 (48%)
|  | Yellow | 16 (25%) |  |  | Yellow | 3 (4%)
|  | Red | 17 (27%) |  |  | Red | 24 (38%)
|  | White (non-participation) | 6 (10%) |  |  | White (non-participation) | 6 (10%)
|  |  | Assessment | Progress Report | Next Steps |  | Final Report
Coop | District | School | October 31, 2014: Technology Readiness Assessment (see Tab 3 for tech specs) | January 30, 2015: School Implementation | February 1 - May 29 2015: School Implementation | School | May 29, 2015: School Implementation
GRREC | Adair County | Adair County High School | Compatible | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff, CCRC and other staff are using the appropriate WIN products with a high degree of fidelity, WIN reports are being generated and used to guide implementation | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Adair County High School | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff, CCRC and other staff are using the appropriate WIN products with a high degree of fidelity, WIN reports are being generated and used to guide implementation. Plans to continue and increase use for 15-16 school year and begin earlier on in the year.
GRREC | Campbellsville | Campbellsville High School | Compatible | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Campbellsville High School | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff. Plan to continue use for 15-16 year and possbily increase Soft Skills as part of year-long employability class.
GRREC | Campbellsville | Campbellsville Middle School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (8th graders will use WIN at the ATC only) | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Campbellsville Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (8th graders will use WIN at the ATC and in high school classes only).
OVEC | Carroll County | Carroll County Middle School | Compatible | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Carroll County Middle School | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff. Plan to continue use in Careers class for 15-16 year.
OVEC | Carroll County | Carroll County High School | Compatible | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Carroll County High School | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff
GRREC | Cloverport Ind. | Frederick Fraize High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email in March | Frederick Fraize High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff. Plan to continue WIN use next year and possibly increase to include mentor teachers who support students in career-readiness.
GRREC | Cloverport Ind. | Frederick Fraize Middle School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email in March | Frederick Fraize Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff. Plan to continue WIN use next year and possibly increase to include mentor teachers who support students in career-readiness.
GRREC | Green County | Green County High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (ATC has wide use as the high school plans to use WIN during RtI time in coming weeks | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email in March | Green County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (ATC has wide use; high school plans to require Soft Skills be completed before allowing student to job shadow)
GRREC | Green County | Green County Middle School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (8th graders will use WIN at the ATC only) | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email in March | Green County Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (8th graders will use WIN at the ATC only)
GRREC | Hart County | Hart County High School | Compatible | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email in March | Hart County High School | Strong school-level buy-in and support for the implementation strategy, Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff; will use for WorkKeys, Compass and KOSSA prep again next year after having great results this year.
OVEC | Henry County | Henry County High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by building staff in Career-Readiness and Enlgish classes | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Henry County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by building staff in Career-Readiness and Enlgish classes
GRREC | Logan County | Logan County High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff for use during RtI time (also, ATC will have training on 2/2 and plans to use WIN for WorkKeys prep in coming weeks) | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email every 3 weeks | Logan County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff for use during RtI time (CATS time) for WorkKeys prep. Will include in CATS time again in 15-16 school year.
GRREC | Metcalfe County | Metcalfe County Middle School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Metcalfe County Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff as part of careers class (CRC goal to reach level 3 or higher and also complete SS Teamwork module, use MSC for career exploration)
GRREC | Monroe County | Monroe County High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Monroe County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff for WorkKeys prep. Plan to use in similar manner in 15-16 school year but also have freshman use Soft Skills and more intentional use of SS related to KOSSA prep
OVEC | Owen County | Owen County High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Owen County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff mainly in small groups and one-on-one for WorkKeys prep and career exploration. Had great WorkKeys pass rates. Plan will be similar in 15-16 school year.
GRREC | Owensboro Ind. | Owensboro High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Owensboro High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by other building staff in CTE classes and during enrichment time for WorkKeys prep. Plan to continue use in same manner 15-16 school year.
GRREC | Russell County | Russell County High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff - students are using WIN in ATC classes | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Russell County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff - students are using WIN in ATC classes only with high fidelity and highest WorkKeys pass rates to date.
GRREC | Russell County | Russell County Middle School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by building staff in Career-Readiness class | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Russell County Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff as part of careers class (CRC goal to reach level 3 or higher and also complete SS Teamwork module, use MSC for career exploration)
GRREC | Simpson County | Franklin-Simpson High School | multiple requests made | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Franklin-Simpson High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff in small groups for WorkKeys prep solely; Expect similar use in 15-16 school year.
GRREC | Taylor County | Taylor County High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Taylor County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (broad use at ATC and in pathways classes at high school). Plan will be simlar in 15-16 school year.
OVEC | Trimble County | Trimble County High School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Trimble County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff as part of careers class (CRC goal to reach level 3 or higher and also complete SS Teamwork module, use MSC for career exploration)
GRREC | Union County | Union County High School | Compatible | Strong school-level buy-in and support for the implementation strategy, Strong district-level buy-in and support for the school implementation strategy | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Union County High School | Strong school-level buy-in and support for the implementation strategy, Strong district-level buy-in and support for the school implementation strategy. Plan to use WIN even more during enrichment time with freshman in SS, seniors focus on WorkKeys, English teacher uses SS as part of Capstone project.
GRREC | Union County | Union County Middle School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Union County Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff. Plan to keep using WIN in study skills/computer class.
GRREC | West Point | West Point Middle School | Compatible | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email every 3 weeks | West Point Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff. Will use similarly next year on "WIN Wednesdays" for career exploration.
GRREC | Daviess County | Apollo High School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase in February after recent training for CTE teachers | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email in March | Apollo High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff. Plan to use for career exploration with 10th graders again next year and in CTE Classes as prep for WorkKeys and KOSSA
GRREC | Daviess County | Daviess County High School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase in coming weeks as all students will begin logging in during Advocate Group time | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email in March | Daviess County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff. Plan to use for career exploration with 10th graders again next year and in CTE Classes as prep for WorkKeys and KOSSA
GRREC | Logan County | Auburn Elementary School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase once new teacher has been trained in courseware mid-February | Host Training in mid-February, monitor data on weekly basis, virtual/on-site support as needed, check-in via email in March | Auburn Elementary School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (students use WIN in new class taught by Family Resource Director). Plans to increas use to CRC and SS next year and expand to Olmstead and Chandler's.
GRREC | Monroe County | Monroe County Middle School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase in spring as students begin transition plans for entering high school working with Mitzi Holland, CCRC | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email every 3 weeks | Monroe County Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (8th graders will use WIN in Careers class).
OVEC | Spencer County | Spencer County High School | Compatible | Lack of clear building-level or district-level by-in and support for implementation as well as very limited technology | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email every 3 weeks | Spencer County High School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff (CTE Teachers) as part of WorkKeys prep
OVEC | Trimble County | Trimble County Middle School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase once teacher has been trained in courseware in early February | Host Training in early February, monitor data on weekly basis, virtual/on-site support as needed, check-in via email in March | Trimble County Middle School | Strategy is based on school-identified needs and appropriate WIN tools are being used/accessed by CCRC and other building staff as part of related arts class for all grade levels. Plan to use WIN as part of the careers class again in 15-16 school year.
OVEC | Shelby County | Martha Layne Collins High School | multiple requests made | Still minimal usage by CCRC or other staff, but indication is that usage will increase | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email every 3 weeks | Martha Layne Collins High School | Lack of clear building-level buy-in and support for implementation though with drop in Career Readiness scores for district, building-level administration regrouping to increase use and monitoring for 15/16 school year
OVEC | Shelby County | Shelby County High School | multiple requests made | Still minimal usage by CCRC or other staff, but indication is that usage will increase | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email every 3 weeks | Shelby County High School | Lack of clear building-level buy-in and support for implementation though with drop in Career Readiness scores for district, building-level administration regrouping to increase use and monitoring for 15/16 school year
OVEC | Owen County | Maurice Bowling Middle School | Compatible | School staff not willing to engage the WIN products, though efforts made by Anne Kline, CCRC, due to limited technology and no clear time in schedule for implementation | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email every 3 weeks | Maurice Bowling Middle School | Lack of clear understanding about what the WIN products can do to advance CCR in school/district, though efforts made by Anne Kline, CCRC. Likely to use minimally again next year in Practical Living class and Soft Skills as part of one science class.
GRREC | Hart County | Bonnieville Elementary School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase as CCRC makes school visits this spring | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email every 3 weeks | Bonnieville Elementary School | Schools started off with good intentions but has since stopped its implementation of the WIN products,as part of career exploration/planning led by CCRC, Brenda Line, but so many snow days reduced time available and this wasn't able to happen as planned. Hopes to use with students in 15-16.
GRREC | Hart County | Cub Run Elementary School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase as CCRC makes school visits this spring | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email every 3 weeks | Cub Run Elementary School | Schools started off with good intentions but has since stopped its implementation of the WIN products,as part of career exploration/planning led by CCRC, Brenda Line, but so many snow days reduced time available and this wasn't able to happen as planned. Hopes to use with students in 15-16.
GRREC | Hart County | Legrande Elementary School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase as CCRC makes school visits this spring | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email every 3 weeks | Legrande Elementary School | Schools started off with good intentions but has since stopped its implementation of the WIN products,as part of career exploration/planning led by CCRC, Brenda Line, but so many snow days reduced time available and this wasn't able to happen as planned.Hopes to use with students in 15-16.
GRREC | Hart County | Memorial Elementary School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase as CCRC makes school visits this spring | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email every 3 weeks | Memorial Elementary School | Schools started off with good intentions but has since stopped its implementation of the WIN products,as part of career exploration/planning led by CCRC, Brenda Line, but so many snow days reduced time available and this wasn't able to happen as planned. Hopes to use with students in 15-16.
GRREC | Hart County | Munfordville Elementary School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase as CCRC makes school visits this spring | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email every 3 weeks | Munfordville Elementary School | Schools started off with good intentions but has since stopped its implementation of the WIN products,as part of career exploration/planning led by CCRC, Brenda Line, but so many snow days reduced time available and this wasn't able to happen as planned. Hopes to use with students in 15-16.
OVEC | Henry County | Henry County Middle School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase after training teachers at end of February | Monitoring data on weekly basis, virtual/onsite support as needed, check-in via email every 3 weeks | Henry County Middle School | School staff not willing to engage the WIN products this school year due to number of initiatives in district.
OVEC | Spencer County | Spencer County Middle School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase when students begin working in career exploration related to reality store in the spring | Monitoring data on weekly basis, virtual/on-site support as needed, check-in via email in March | Spencer County Middle School | School staff not willing to engage the WIN products this school year due to number of initiatives in district. New CCRC, T.Jai Rogers hopes to get 8th graders in WIN for 15-16 school year.
GRREC | Taylor County | Taylor County Middle School | Compatible | Still minimal usage by CCRC or other staff, but indication is that usage will increase after meeting with principal on 2/9 | Continue attempts to get face-to-face meeting | Taylor County Middle School | School staff not willing to engage the WIN products, though efforts made by Christy, CCRC, due to being District of Innovation and having too many resources to employ, according to school leaderhip. Not likely to use in 15-16.
GRREC | Adair County | Adair County Middle School | Compatible | School staff not willing to engage the WIN products, though efforts made by Robin Loy, CCRC, due to extremely limited technology and outdated infrastructure onsite (plans in place to update but may be spring before improvements are made/complete) | Contact in summer to engage for 15-16 school year | Adair County Middle School | School staff not willing to engage the WIN products, though efforts made by Robin Loy, CCRC, due to extremely limited technology and outdated infrastructure onsite. Major improvements in late spring and early summer will position teachers to use WIN next year, at least myStrategic Compass. Already interest in having 8th graders use WIN 15-16.
GRREC | Caverna Ind. | Caverna High School | Compatible | Schools started off with good intentions but has since stopped its implementation of the WIN products, though efforts made by Pam Waters, CCRC, because time allotted for WIN was delayed in getting added to school day. May pick up in February | Monitoring data on weekly basis, check-in via email monthly, virtual/on-site support as needed | Caverna High School | Schools started off with good intentions but has since stopped its implementation of the WIN products, though efforts made by Pam Waters, CCRC, because time allotted for WIN was delayed in getting added to school day. Schedule change slated for 15-16 school year to include built-in enrichment time where WIN will be one of suggested resources.
GRREC | Caverna Ind. | Caverna Middle School | Compatible | Schools started off with good intentions but has since stopped its implementation of the WIN products, though efforts made by Pam Waters, because have not found time to include WIN in school day yet for 8th graders. | Monitoring data on weekly basis, check-in via email monthly, virtual/on-site support as needed | Caverna Middle School | Schools started off with good intentions but has since stopped its implementation of the WIN products, not likely to implement in 15-16.
GRREC | Daviess County | College View Middle School | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Susan Colbert and Jeremy Camron, CCRCs | Contact in summer to engage for 15-16 school year | College View Middle School | School staff not willing to engage the WIN products this school year due to number of initiatives in district. Not likely to use in 15-16.
GRREC | Daviess County | Daviess County Middle School | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Susan Colbert and Jeremy Camron, CCRCs | Contact in summer to engage for 15-16 school year | Daviess County Middle School | School staff not willing to engage the WIN products this school year due to number of initiatives in district. Not likely to use in 15-16.
GRREC | Daviess County | F T Burns Middle School | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Susan Colbert and Jeremy Camron, CCRCs | Contact in summer to engage for 15-16 school year | F T Burns Middle School | School staff not willing to engage the WIN products this school year due to number of initiatives in district. Not likely to use in 15-16.
GRREC | Logan County | Adairville Elementary School | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Alison Frederick, CCRC | Contact in summer to engage for 15-16 school year | Adairville Elementary School | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Alison Frederick, CCRC.
GRREC | Logan County | Chandlers Elementary School | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Alison Frederick, CCRC | Contact in summer to engage for 15-16 school year | Chandlers Elementary School | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Alison Frederick, CCRC. New Family Resource Direcctor plans to use WIN with 8th graders 15-16 (CRC, SS, MSC).
GRREC | Logan County | Lewisburg Elementary School | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Alison Frederick, CCRC | Contact in summer to engage for 15-16 school year | Lewisburg Elementary School | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Alison Frederick, CCRC.
GRREC | Logan County | Olmstead Elementary School | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Alison Frederick, CCRC | Contact in summer to engage for 15-16 school year | Olmstead Elementary School | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Alison Frederick, CCRC. New Family Resource Direcctor plans to use WIN with 8th graders 15-16 (CRC, SS, MSC).
GRREC | Metcalfe County | Metcalfe County High School | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Eric Sexton, CCRC | Contact in summer to engage for 15-16 school year | Metcalfe County High School | School staff not willing to engage the WIN products this school year due to number of initiatives in district, though efforts made by Eric Sexton, CCRC. KOSSA Alignment spurred new conversation with CTE teacher about possibly ustilizing Soft Skills next year but confidence is not strong that this will happen.
GRREC | Owensboro Ind. | Owensboro Middle School North | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district | Contact in summer to engage for 15-16 school year | Owensboro Middle School North | School staff not willing to engage the WIN products this school year due to number of initiatives in district.
GRREC | Owensboro Ind. | Owensboro Middle School South | Compatible | School staff not willing to engage the WIN products this school year due to number of initiatives in district | Contact in summer to engage for 15-16 school year | Owensboro Middle School South | School staff not willing to engage the WIN products this school year due to number of initiatives in district.
OVEC | Shelby County | Shelby County East Middle School | multiple requests made | School staff not willing to engage the WIN products though multiple attempts have been made to engage school | Contact in summer to engage for 15-16 school year | Shelby County East Middle School | School staff not willing to engage the WIN products though multiple attempts have been made to engage school.
OVEC | Shelby County | Shelby County West Middle School | multiple requests made | School staff not willing to engage the WIN products though multiple attempts have been made to engage school | Contact in summer to engage for 15-16 school year | Shelby County West Middle School | School staff not willing to engage the WIN products though multiple attempts have been made to engage school.
GRREC | Simpson County | Franklin-Simpson Middle School | multiple requests made | School staff not willing to engage the WIN products, though mulitple attempts have been made to connect with building staff | Contact in summer to engage for 15-16 school year | Franklin-Simpson Middle School | School staff not willing to engage the WIN products, though mulitple attempts have been made to connect with building staff.

## Sheet1
Green | 24 (43%)
Yellow | 15 (27%)
Red | 17 (30%)